## SOW Defensibility Scorecard
SOW Technical Defensibility Calculator
Evaluate pre-award Statement of Work (SOW) drafts against 15 binary checkpoints.
Project Name: | [ Insert Project / Solicitation Name ] |  | Evaluator: | [ Name / Role ]
Date Evaluated: | 2026-11-01 |  | Total Score: | 10
|  |  | Defensibility Tier: | CONTRACTUALLY DEFECTIVE (Halt Procurement)
# | Defensibility Checkpoint | Score (1=Pass, 0=Fail) | Validation Standard & Contractual Guidance | Evaluation / Redline Remediation Notes
1 | Explicit Out-of-Scope Boundaries (Negative Scope) | 1 | Contract includes a clear list of what the vendor will NOT build (unsupported legacy software, excluded third-party APIs).
2 | System Interface Definitions | 0 | Documented rules, data schemas, and response-time SLAs for every external system connection point.
3 | Data Migration Standards | 1 | Responsibilities for extraction, cleaning, formatting, and loading are explicit; max error rate <= 0.02%.
4 | Automated Approval Gates | 1 | Milestones are approved/paid based on automated testing pass/fail telemetry, not subjective sign-offs.
5 | Real-World Load Testing | 1 | System performance validated via a continuous 24-hour soak test under peak production traffic profiles.
6 | Clear Rejection Timelines | 0 | Buyer has 10-15 business days to review deliverables with formal written technical rejection procedure.
7 | Software Bill of Materials (SBOM) | 1 | Machine-readable CycloneDX v1.5 SBOM provided with every release candidate.
8 | Security Vulnerability Rules | 1 | Pre-delivery zero unmitigated CVSS 7.0+ flaws or CISA Known Exploited Vulnerabilities (KEVs).
9 | Code Maintenance Standards | 1 | Automated scanners verify ISO/IEC 5055 maintainability >= 75 and Technical Debt Ratio <= 5.0%.
10 | Objective Issue Classification | 1 | Errors categorized strictly by operational impact (Severities 1-4) governing mandatory resolution SLAs.
11 | Withheld Payments for Quality Assurance | 1 | 15% rolling retainage on milestone invoices + 10% warranty retainage held 90-180 days post-launch.
12 | Fixed-Work Scope Swaps | 1 | Equal-effort removal of original scope required when adding new feature change requests.
13 | Independent Source Code Verification | 0 | Third-party Level 3/4 escrow verification confirming clean-room build capability without vendor assistance.
14 | Hands-On Knowledge Transfer | 0 | Handoff incomplete until internal team successfully installs, launches, and operates platform via provided manuals.
15 | Full Delivery of Infrastructure Code | 0 | Full legal ownership of deployment scripts, Helm charts, Terraform manifests, and CI pipelines (DFARS 252.227-7014).

## Scoring Tiers & Guidance
ButtonUp SOW Evaluation Tiers & Operational Rules
Score Tier | Status | Required Action / Governance Directive
14 - 15 Points | DEFENSIBLE | Contract contains objective boundaries, automated verification gates, and enforceable commercial remedies. Approved for award.
11 - 13 Points | ELEVATED RISK | Vague language leaves key technical expectations exposed. Requires targeted redrafting of failing clauses before signature.
10 Points or Fewer | CONTRACTUALLY DEFECTIVE | Contract relies heavily on subjective adjectives and lacks automated acceptance criteria. Procurement should halt until restructured.